## Sheet1
DAY | Sprint | Task | Status
2026-07-02 | Sprint 1 | Requirements Gathering and Project Disscussion | completed
2026-07-02 | Sprint 1 | Product Backlog and User Stories | completed
2026-07-02 | Sprint 1 | Dataset Collection and EDA | completed
2026-07-03 | Sprint 1 | Data Cleaning and Preprocessing | completed
2026-07-03 | Sprint 2 | Feature Engineering | completed
2026-07-04 | Sprint 2 | Model Selection and Initial Training | completed
2026-07-04 | Sprint 2 | Model Training and Performance Analysis | completed
2026-07-05 | Sprint 2 | Hyperparamater Tuning | completed
2026-07-05 | Sprint 3 | Model Evaluation | completed
2026-07-06 | Sprint 3 | Prediction Interface Development | In Progress